## Slide 1: WCP52 USB Gain/Phase Analyzer
Low-cost, open-source gain/phase analyzer

## Slide 2: WCP52 USB Gain/Phase Analyzer Key Personnel
Chris Pavlina- EE Student Team Lead
Kaidi Xu- EE Student
Kenneth Zachary- CoE Student
Harrison Owens- CoE Student
Prof. Kyle Temkin- Faculty Advisor
Prof. Maynard - Program Manager
[Pictured Left to Right: Harrison Owens,Kenneth Zachary,
Chris Pavlina, Kaidi Xu]

## Slide 3: WCP52 USB Gain/Phase Analyzer Executive Summary
We are creating a USB driven device that analyzes the frequency response of filters, amplifiers, and control systems and creates a corresponding Bode Plot of the analysis.

## Slide 4: WCP52 USB Gain/Phase Analyzer Context Diagram
2014-10-31 3

## Slide 5: WCP52 USB Gain/Phase Analyzer System Diagram

## Slide 6: WCP52 USB Gain/Phase Analyzer Major Milestones Fall
100% Project Launch: 2012‐09‐21
100% Requirements Analysis / SRR: 2014‐10‐17
100% System Design / SDR: 2014‐10‐31
90% Architectural Design / PDR: 2014‐11‐14
0% Detailed Design / CDR: 2014‐12‐05
0% Interim Presentation: 2014‐12‐12

## Slide 7: WCP52 USB Gain/Phase Analyzer Project Finances: 500$
Item | Expended | Actual | Est. to Compl. | Est. at Compl.
Synthesizer | $60 | $60 | $0 | $60
Input | $0 |  | $40 | $40
Detector | $0 |  | $50 | $50
Output | $0 |  | $50 | $50
Power supply | $0 |  | $20 | $20
Final PCB | $0 |  | $120 | $120
Enclosure | $0 |  | $30 | $30
Misc/re-spins | $0 |  | $100 | $100
Total | $60 | $60 | $410 | $470

## Slide 8: WCP52 USB Gain/Phase Analyzer Major Issues
Still need to characterize RF switch – parts were late