## Slide 1: Gain and Phase Analyzer Interim Report
2014, December 12th
Notes: Kaidi

## Slide 2: Gain and Phase Analyzer
Purpose
Requirements
Design
Schedule
Budget
Next Steps
Notes: Kaidi

## Slide 3: Purpose
Test the performance of filters, amplifiers
Generate Bode plot with
amplitude and phase
Notes: Kaidi

## Slide 4: Uses
Applications
Signal filters
Signal amplifiers
Control systems
Education
Testing and characterizing circuits
Design
Notes: Chris

## Slide 5: Why?
Current state of industry
  Large
  Expensive
  Learning curve
  Students can’t see how it works!
Our Goal
  Portable
  Cost around $200
  Easy to use for students and teachers
  Open source
Notes: Chris

## Slide 6: Requirements
Notes: Chris

## Slide 7: Design — Software
Notes: Harrison

## Slide 8: Design — Microcontroller
Notes: Harrison

## Slide 9: Design — Signal Generation
Notes: Ken

## Slide 10: Design — Signal Output
Notes: Ken

## Slide 11: Design — Detection
Notes: Chris

## Slide 12: Design — Phase Detection
Notes: Chris

## Slide 13: Timeline
Notes: Harrison

## Slide 14: Schedule
Item | Start Date | End Date | Percent Complete
Specification | 2014-10-03 | 2014-10-17 | 100%
Development Plan | 2014-10-17 | 2014-10-31 | 100%
Architecture | 2014-10-31 | 2014-11-14 | 100%
Interim Report | 2014-11-14 | 2014-12-05 | 100%
Proto. built | 2014-11-14 | 2014-12-05 | 100%
Proto. firmware | 2014-11-10 | 2014-12-05 | 100%
Notes: Harrison

## Slide 15: Budget
Item | Expended | Actual | Estimated to Completion | Estimated at Completion
Synthesizer | $60 | $60 | $0 | $60
Input | $70 | $70 | $0 | $70
Output amp. | $66 | $66 | $0 | $66
Power supply | $0 | $0 | $0 | $0
Final build | $0 |  | $120 | $120
Enclosure | $0 |  | $30 | $30
Misc/re-spins | $0 |  | $100 | $100
Total | $196 | $196 | $250 | $446
Notes: Harrison

## Slide 16: Next Steps
Hardware
Combine prototypes into a final product
Software
Finish firmware with full analysis capability
Write PC software that receives and plots data
Notes: Ken

## Slide 17: Conclusion
Product can capture Bode plots
Uses signal synthesizer, output amplifier, input frontend, ADC, and microcontroller
These have been prototyped and tested
Notes: Kaidi

## Slide 18: Demo

## Slide 19: Questions?
Notes: Kaidi