## Slide 1: WCP52 USB Gain/Phase Analyzer
Low-cost, open-source gain/phase analyzer

## Slide 2: WCP52 USB Gain/Phase Analyzer Key Personnel
Chris Pavlina- EE Student Team Lead
Kaidi Xu- EE Student
Kenneth Zachary- CoE Student
Harrison Owens- CoE Student
Prof. Kyle Temkin- Faculty Advisor
Prof. Maynard - Program Manager
[Pictured Left to Right: Harrison Owens,Kenneth Zach,
Chris Pavlina, Kaidi Xu]

## Slide 3: WCP52 USB Gain/Phase Analyzer Executive Summary
We are creating a USB driven device that analyzes the frequency response of filters, amplifiers, and control systems and creates a corresponding Bode Plot of the analysis.

## Slide 4: WCP52 USB Gain/Phase Analyzer Context Diagram

## Slide 5: WCP52 USB Gain/Phase Analyzer System Diagram

## Slide 6: WCP52 USB Gain/Phase Analyzer System Architecture
Hardware:
Signal generator: Synthesizes signal to stimulate the Device Under Test (DUT)
Input detector: Measures the signal returned from the DUT
Microprocessor: Controls other components, computes measurements, communicates with PC Software
PC Software:
Sends control signals to hardware
Receives data, formats display
Possibly performs post-processing

## Slide 7: WCP52 USB Gain/Phase Analyzer Meeting Requirements
Source frequency range: entirely covered by one part; easy to achieve
Received dynamic range: entirely covered by one part; circuitry may require RF shielding
PC interface: USB, CDC (communications device class)
Most other requirements are software requirements

## Slide 8: WCP52 USB Gain/Phase Analyzer Manufacturing Feasibility
The entire system consists of a single Printed Circuit Board, assembled with typical SMT assembly techniques, and inserted into a premade enclosure. All parts are easily available.

## Slide 9: WCP52 USB Gain/Phase Analyzer Risks
Schedule:
PCBs slow to manufacture. Subsystems are developed in parallel; development can continue while waiting.
Documentation:
Parts that we are using are not always well documented

## Slide 10: WCP52 USB Gain/Phase Analyzer Major Milestones Fall
100% Project Launch: 2012‐09‐21
100% Requirements Analysis / SRR: 2014‐10‐17
100% System Design / SDR: 2014‐10‐31
100% Architectural Design / PDR: 2014‐11‐14
0% Interim Presentation: 2014‐12‐12

## Slide 11: WCP52 USB Gain/Phase Analyzer Project Finances: 500$

## Slide 12: WCP52 USB Gain/Phase Analyzer Major Issues
Schedule. Project is complicated, relies on many external services (PCB fabrication, parts, sampled parts)